## Sheet1
Library Asisstants Management System Prodcut Backlog
Story ID | Request by | Description | Sprint # | 1 | 2 | 3 | 4 | 5 | 6
|  |  | Effort needed for Release 1 as in the beginning of the sprint | 280 | 0 | 0 | 0 | 0 | 0
1 | Eirc | Set up continuous integration system |  | 10 | 0 | 0 | 0 | 0 | 0
2 | Eric | Create application skeleton |  | 10 | 0 | 0 | 0 | 0 | 0
3 | Eirc | Create the Library Assistant Management System project on the Github |  | 10 | 0 | 0 | 0 | 0 | 0
4 | litao | design the basic skeleton of the Library Assistants Management System |  | 20 | 0 | 0 | 0 | 0
|  | design the index of the website(首页) |  | 10 | 0 | 0 | 0 | 0
Sprint 1 |  | Create the initial simple prototype of the Library Assistants Management System website
5 | litao | provide an model for assistants and admins to login |  | 15 | 0 | 0 | 0 | 0
6 | Product Owner | An assistant manages his/her own basic information and working information |  | 45 | 0 | 0 | 0 | 0
7 | Product Owner | An admin manages his/her own information and assistants information |  | 45 | 0 | 0 | 0 | 0
8 | Product Owner | Recruit new assistants |  | 30 | 0 | 0 | 0 | 0
Sprint 2 |  | Complete four models of the Library Assistant Management System
9 | Product Owner | news about assistants model |  | 20 | 0 | 0 | 0 | 0 | 0
10 | Product Owner | A visitor leaves messages and gives advice |  | 15 | 0 | 0 | 0 | 0 | 0
11 | Product Owner | show elegant demeanor of assistants |  | 15 | 0 | 0 | 0 | 0
12 | Product Owner | display working scheme of assistants |  | 15 | 0 | 0 | 0 | 0
13 | Product Owner | An admin updates news of the websites |  | 20 | 0 | 0 | 0 | 0
Sprint 3 |  | complete most parts of the system website
Release 1
Sprint 4
Release 2
|  | Effort in the whole backlog |  | 280 | 0 | 0 | 0 | 0 | 0